- Terms Of Reference

- Democracy & Governance [DG] BRIDGE

- DEMOCRATIC GOVERNANCE (DG) CURRICULUM DEVELOPMENT

This TOR outlines the process undertaken to develop a governance curriculum for the DG BRIDGE project and the specific deliverables required of the consultant who is contracted to assist in writing the a governance curriculum [‘Governing Ourselves’] for the DG BRIDGE project.

- Background:

The goal of DG BRIDGE is to promote and support democracy and governance through facilitating dialogue, learning, resources and networks in the Asia Pacific region and is targeted at a wide range of stakeholders including government representatives and officials at all levels, community organisers and leaders, policy makers and thinkers, civil society organisation leaders, staff of international agencies, business leaders, civic education professionals, emerging young leaders and so on.

The DG BRIDGE programme is funded by AusAID (Australian Agency for International Development) and UNDEF (United Nations Democracy Fund), and is being showcased and implementing in the Asia Pacific region in 2010.

It is designed to be of benefit to those agencies engaged in supporting:

- State and non-state capacity development for democratic governance,

- Increased democratic space, social accountability and voice at national and sub-national levels

- Parliamentary development and increased capacity of lawmakers

- Civil society development and increased civic participation

- Public awareness of human rights and democracy

- Gender & Human Rights Programmes

- Youth Participation & Empowerment

The governance curriculum is being written in 2010 by a diverse group of specialists (curriculum development and democratic governance specialists) from around the world.

The programme in 2009 focused on the development of the democracy curriculum currently entitled ‘Democracy in Our Place’, [DIOP] which in reality is a multi-stakeholder facilitated process where a range of state and non-state actors explore the concepts of democracy and governance [learning], looking at how these might be applied at both the policy and practice levels in each country [localizing] and planning for joint action and change [leading] resulting in increased participants’ knowledge, skills and attitudes at a minimum level and in increased civic participation and democratic governance at the optimum level. The programme pays particular attention to the various Asia/Pacific cultural and political contexts and learning styles.

In 2010 the focus will be on developing the governance curriculum ‘ Governing Ourselves’ which will then be merged with the DIOP curriculum developed in 2009, to result in one overall DG curriculum capable of being customised by a regional [and eventually a global] team of trained facilitators who will be mentored to facilitate a tailored version of the curriculum appropriate to specific national and local contexts.

- Programme Philosophy

While this is a TOR for the development of a training curriculum it should be noted that the DG curriculum is intended neither as a standard off-the-shelf curriculum, nor is it simply focussed on training alone.  Rather, its designed as a multi-stakeholder facilitated process [based around Paulo Freire’s pedagogy and participative action learning principles] where a range of state and non-state actors explore the concepts of democracy and governance [learning], looking at how these might be applied at both the policy and practice levels in each country [localizing] and planning for joint action and change [leading] resulting in increased participants’ knowledge, skills and attitudes at a minimum level and in increased civic participation and democratic governance at the optimum level. So in all our curriculum design we are planning for learning and cooperative action as the optimum, but with the understanding by facilitators that learning as an outcome alone is still a highly desirable result. The methodology is participatory, and uses experiential pedagogies that aims to develop skills, attitudes and knowledge around the topic areas. So facilitators and participants have a large say in what topics are to be covered and how they are to be covered.

- Target Group

The target group for the Governance Curriculum is the same as for the DiOP module: state and non-state actors, ranging from parliamentarians to local and international civil society actors to government officials, media and the judiciary. That is, people either working in the fields of democracy or governance, or who simply want to be more informed or engaged in the political life and/or governance of the environments in which they live and work. Target groups may be homogenous (eg public servants from an electoral management body) or mixed. Ideally a mixed group enhances the knowledge sharing between the different topics and expertise of the participants.

- Structure & Format

This governance curriculum is in reality an extension of the “Democracy in our Place” (DiOP) module and because it will be merged with it in the future will be structured in a similar format to the DiOP module. The DiOP Facilitators Sourcebook contains over 50 lesson plans, from which facilitators tailor workshops for their specific target group. Workshops are usually for 5 days duration. The overall curriculum framework for the “Governing Ourselves” [GO] curriculum includes 1 introductory session, and then 8 governance ‘theme’ sessions which will each contain 1-3 learning activities. The core deliverable of this TOR is the development of the curriculum [learning outcomes, background reading and learning activities/lesson plans] for each of these 9 sessions. These will be published in the GO Facilitators Sourcebook – in a similar format to DiOP activities. Facilitators will customise according to the needs of the target group, so that they can focus/concentrate on topics that interest them.

Ideally, the DiOP and GO modules are intended to be conducted over 2 weeks (8 days – 4 days each) – one full week and then a second full week either immediately following the first week or after several weeks break.

- Scope of the GO Curriculum

The GO module is intended to be an introductory exploration of all democratic governance themes. This is because it is a short professional development course, and a multi-stakeholder facilitated dialogue/planning process, and it is not an academic course of study. Facilitators and participants will jointly choose the level of depth that they explore for each of the 8 main topic areas.

The purpose of the GO curriculum will therefore be to provide a broad understanding of all the key elements of democratic governance, and to explore the underlying principles, common elements, current or emerging thinking on best practices, and the common challenges facing participants in promoting more democratic governance, mainly in [but not limited to] developing country contexts.

Because the curriculum can be tailored to various specific contexts and target groups, it may be for example that a particular target group of participants are all from civil society organisations, and they want to gain an overview of the other governance areas (other than the one they already work in).

Alternatively, there may be a diverse group of participants from government, media, civil society and the private sector, each with in-depth knowledge of how their own individual area relates to governance – but in this GO workshop, they will have come together to explore all the topic areas of governance.

The curriculum designed will therefore need to take account of these range of possible delivery modes and allow for a range of target groups.

- The Facilitators

The curriculum design consultant should note that facilitators using this curriculum will be usually very experienced in facilitation and will have undergone an extensive accredited training  of facilitators [TOF] process for the DG curriculum which includes regional training as well as mentoring, coaching and contextualisation in country. They will also have commissioned a specific country case study, outlining the key governance and democracy challenges in the country where the curriculum is to be delivered at the preparation stage of each national workshop and will be able to use this when preparing to deliver each of the learning activities you will design.

- Themes & Topics Overview

- Curriculum designers will be assigned one or more of the following Topics:

- A: Introduction to Democratic Governance

This 3- hour session should provide activity learning outcomes, participatory learning activities and core reading around the following themes:

- Definitions - democracy? democratic governance?, governance? good governance? why DG?

- What are the key elements of democratic governance and how do they link together?

- Underlying principles of democratic governance

- Identifying Specific Challenges

- Governance assessments, etc

The 8 Key Topics (Overview) – [See Democratic Governance Curriculum Matrix” attached]

- Constitutions

- Electoral Systems and Processes

- Parliamentary Development

- Access to Information & Media

- Local Governance & Decentralization

- Public Administration Reform & Anti-Corruption

- Justice systems & Rule of Law

viii.Civil Society Development & Civic Participation

- The Cross-Cutting Themes

Consideration of the following cross-cutting themes should be integrated across each of the 8 topic areas:

  - International Principles [Human rights, Gender Equity, Participation & Empowerment etc]

- Accountable Institutions

- Capacity Development

- Political Economy

- The Deliverables:

- The PRIMER: A 5-page introduction on one [or more as agreed] of the topic areas [target audience: participants and facilitators to gain greater understanding of topic]. Each ‘primer’ is designed to be an introduction or overview to each of the topics, which includes the key elements/concepts of the topic, a description of how the institution/topic functions in a democracy (emerging and consolidating), what principles underlie the proper functioning of this institution/process, what emergent thinking/ideas exist, what key challenges exist, etc. Examples of both challenges and learning from real countries should be included, but the purpose is more to explain the building blocks and key features of the institutions/processes in generic terms.

- Learning Activities: X 3 participatory activities for teaching/facilitating an introductory participatory session in the topic are preferably using the case study and primer and lasting approximately 3 hours in total.

- ‘Must Read’ Resources: further reading, articles, websites, etc eg key organisations, etc for each 8 areas

6. Fees, Duration & Management

Fees for consultants: AUD$500 per day (and by output, as negotiated)

Time frame: It is expected that 7-10 days [to be agreed] will be sufficient to provide the deliverables and the timeframe for delivery is August  - September 2010

| End July | Call for Expressions of Interest |
| --- | --- |
| August | Commission writers |
| August | First draft deadline 20 Aug. Return drafts by 25 Aug. Final draft due 3 Sept |
| September | DG BRIDGE will send drafts to curriculum advisors. Consultants should allow 1-day for any final revisions requested by DG advisors |

The selected writers will work under the direction of the DG BRIDGE Coordinator who will have overall responsibility for coordinating and managing each of the tasks associated with the development of the materials and for ensuring that the project is completed to an acceptable standard, on time and within budget. Democratic governance advisors from various organisations will be invited to comment on the draft materials throughout the writing process.

7. Expressions of Interest

Expressions of interest are invited from consultants with a blend of curriculum development and training  experience coupled with knowledge  and expertise in one [or more] of the key  governance themes listed above and who are available and capable of delivering the outputs specified within the timeframe.

The application form should be completed and submitted, along with the required supporting statements (and referees) and documentation (CV, writing samples) to:

- Submit expressions of interest by 6 August 2010 to

yvonnegoudie@yahoo.com.au, and  yvonne.goudie@aec.gov.au

For background to DG BRIDGE, refer to “DG BRIDGE Overview 2010”, and for the structure of curriculum, refer to the “DG BRIDGE Meta Framework” – attached below.